## Live Local Projects
Sr. No. | Lead Date | Firm/Project Name | Project start date | Project End Date(Deadline) | Project Requirement | Total Price | Milestone-1 | Milestone-2 | Milestone-3 | Milestone-4 | Remaining Payment | Project Status | Remarks
1 |  | Soby Tours and Travels | 2021-06-17 | 2021-07-02 | Website Development | 11900 | 800 | 8000 | 3100 | 3100 | 0 | Open | Server charges not given by clients
2 | 2021-06-24 | NM Balaji Interior Designing | 2021-06-30 | 2021-07-15 | Website Development | 13100 | 5000 | 8100 | 1400 |  | 0 | close | Delivered
3 | 2021-06-11 | Raj Synthetics(Textile Industry) |  |  | Website Development | 8260 |  |  |  |  | 8260 | Open | Client has Design Issue
4 | 2021-05-29 | Season Tours and Travels | 2021-07-23 | 2021-08-07 | Website Development | 10620 | 5310 | 5310 |  |  | 0 | Close | All credential Source code has been sent to client
5 | 2021-07-26 | R R Transportation | 2021-08-01 | 2021-08-16 | Website Development | 11000 | 11000 |  |  |  | 0 | Close | Website is at Last stage
6 | 2021-09-15 | Breathe Branding | 2021-09-23 | 2021-10-04 | Website Designing | 33185 | 33185 |  |  |  | 0 | close | Design is In Under process
7 |  | contractor ji | 2021-10-07 | 2021-11-26 | Back-end Development | 35000 | 17500 |  |  |  | 17500 | open
8 | 2021-09-27 | Seven3.ai private limited | 2021-10-06 | 2021-10-13 | Website Development (Phase-1) | 20390 | 5100 | 7290 |  |  | 8000 | open | Website Development is done For SEO he will let us know further
9 | 2021-10-05 | KNUS Tyre | 2021-10-07 | 2021-10-13 | Website Development | 11000 | 4000 | 7000 |  |  | 0 | close
10 | 2021-11-11 | Mangala Diagnostic center | 2021-11-30 | 2021-12-10 | Website Development | 9440 | 4000 |  |  |  | 5440 | open
11 | 2021-11-01 | indiadox | 2021-12-16 |  | Website Designing | [5 empty] | 0
Formulas:
Project End Date(Deadline) = [Project start date]+15

## Tasks Detail
Sr. No. | Lead Date | Firm/Project Name | Project start date | Project End Date(Deadline) | Project Requirement | Total Price | Mildstone-1 | Mildstone-2 | Mildstone-3 | Remaining Payment | Project Status | Remarks
1 | 2021-06-20 | KD Ruber | 2021-07-23 | 2021-08-07 | Website Design | 4500 | 2500 | 2090 |  | -90 | close | need to make one more inner page and banner also
2 | 2021-07-22 | Fashion site | 2021-07-23 | 2021-07-24 | Page design | 1000 | 1000 |  |  | 0 | close | payment has been sent from Harlin's account
3 | 2021-07-24 | Fashion site | 2021-07-24 | 2021-07-25 | Page design | 1000 | 1000 |  |  | 0 | close | payment has been sent in feni's account
4 | 2021-07-31 | Fashion site | 2021-07-31 | 2021-08-01 | Page design | 1000 | 1000 |  |  | 0 | close | payment has been sent in feni's account
5 | 2021-08-09 | Fashion site | 2021-08-09 | 2021-08-11 | Homepage design | 1000 | 1000 |  |  | 0 | close | payment has been sent in feni's account
6 | 2021-08-14 | Fashion site Homepage and contact us | 2021-08-14 | 2021-08-16 | Homepage design and contact us | 2000 | 2000 |  |  | 0 | open | payment has been sent in feni's account
7 | 2021-06-20 | KD Ruber |  |  | Total 5 banner+1 brochure+1 web page | 2600 | 2600 |  |  | 0 | close | payment hase been sent in apexa's account
8 | 2021-06-20 | KD Ruber | 2021-08-19 | 2021-08-21 | 1 web page | 800 |  |  |  | 800 | open
9 | 2021-08-14 | Fashion site FAQ | 2021-09-02 | 2021-09-04 | 1 web page | 1000 | 1000 |  |  | 0 | open | payemnt has be sent in feni's account
10 | 2021-08-25 | cake shop | 2021-08-27 | 2021-09-27 |  | 5300 | 3000 | 2500 |  | -200 | close
11 | 2021-09-08 | Existing task(CC) | 9 /9/21 | 2021-09-18 | changes | 6500 |  |  |  | 6500 | open | work is under process
12 | 2021-09-30 | Shopify Tasks | 2021-09-30 | 2021-10-01 | Change Images | 3000 | 1000 | 2000 |  | 0 | close
13 | 2021-09-30 | Contact form task | 2021-10-01 | 2021-10-01 | drop down box, add image | 300 | 300 |  |  | 0 | close
12 | 2021-12-16 | Image culling | 2021-12-16 | 2021-12-20 | Website Designing | 1000 | 1000 |  |  |  | 0 | close
13 | 2021-12-16 | image culling(Service page) | 2021-12-21 | 2021-12-24 | Website Designing | 1000 |  |  |  |  | 1000 | open
7010
Formulas:
Project End Date(Deadline) = [Project start date]+15
Project End Date(Deadline) = [Project start date, row above]+1